## Slide 1
NBA Prediction System
Executive Summary
Project Introduction
The NBA Prediction System aims to provide a data-driven solution that forecasts NBA game outcomes. This document outlines the complete project approach, from initial data collection to model development and final deployment. The system will provide predictions including win probabilities, score projections and player performance forecasts in a CSV format.
Business Context
In the sports analytics makret, accurate NBA predictions serves multiple needs:
  Sports media outlets require data-driven content for engagement
  Fantasy sports platforms rely on effective performance projections
  Betting operators rely on accurate proabilistic forecasting
Solution
This project addresses these needs by creating a flexible, consistent and manageable prediction system built on sound data science principles.
Project Scope
The focus of this project will concentrate around the following:
  Collection and processing of historical NBA team and player data
  Development of predictive models for game outcomes and player statistics
  Daily prediction generation system for upcoming games
  Complete documentation and codebase suitable for production implementation
Objectives & Success Criteria
Primary Objectives
  Develop a reliable data pipeline for NBA stats collection and processing
  Create predictive models for game outcomes with measurable accuracy
  Implement player performance prediction capabilities
  Establish a system/program for daily prediciton generation
  Deliver a well doccumented, workable codebase
Key Performance Indicators
  Model Accuracy Metrics:
    Team win prediction: >65% accuracy, log-loss <0.55
    Score prediction: Mean Absolute Error <5.5 points
    Player scoring prediction: Mean Absolute Error <3.5 points
    Player rebounding prediction: Mean Absolute Error <1.5 rebounds
  System Performances:
    Data refresh completed in <15 minutes
    Prediction generation complete in <10 minutes
  Code quality:
    90% test coverage for core functionality
    All modules pass linting standards

## Slide 2
Phase | Milestone | Deliverables | Target Completion
1: Setup & Foundation | Environment & data collection established | Project structure, GitHub repository, initial data collection scripts | Week 1
2. Data Pipeline | Complete data processing system | Team & player stats processors, Feature engineering framework | Week 3
3. Initial Modelling | Basic prediction capability | Team win probability model, model evaluation framework | Week 5
4. Enhanced Modelling | Complete prediction capability | Score prediction model, player performance models, model integration | Week 8
5. Refinement | Production-ready system | Data refresh programmed, daily prediction generator, performance optimization | Week 10
6. Validation & Documentation | Project completion | Final validation report, complete documentation, project presentation | Week 12
NBA Prediction System
Executive Summary
Project Timeline & Milestones

## Slide 3
  Data Collection Strategy:
    Use NBA API for official statistics
    Implement incremental data updates
    Establish data validations checks
  Model Development Method:
    Start with simple baseline models
    Evaluate multiple algorithm approaches
    Utilise cross validation for reliable performance estimation
    Implement feature importance analysis
    Iteratively improve prediction accuracy
  Technical implementation:
    Modular code structure with clear seperation of concerns
    Test-driven development for core functionality
    continuous integration via GitHub actions
    Comprehensive logging and error handling
NBA Prediction System
Executive Summary
Resources
Technical resources:
  Development environment: Python 3.9+, Visual Studio Code
  Version Control: Git, GitHub
  Core libraries: pandas, numpy, scikit-learn, matplotlib, nba_api
  Compute requirements: 16GB RAM recommended for data processing
  Storage: 5GB for historical data and model artifacts
Skills requirements:
  Python programming
  Data manipulation with pandas
  Statistic modelling and machine learning concepts
  Time series analysis
  Sports analytics domain knowledge
Methodology

## Slide 4
Risk | Impact | Probability | Mitigation Strategy
NBA API limitations or changes | High | Medium | Implement backup data sources, create API response caching
Insufficient prediction accuracy | High | Medium | Start with simpler subproblems, establish baseline metrics early
Data Quality Issues | Medium | High | Implement thorough data validations checks
Scope creep | Medium | Medium | Maintain clear project boundaries, implement iterative deliverables
Computing Resource Limitations | Low | Low | Optimize high-computation processes, consider cloud resources
NBA Prediction System
Executive Summary
Risk Assessment
Quality Assurance Plan
Testing Strategy
  Unit Tests for all data processing functions
  Integration tests for completed pipeline
  Backtesting framework for model evaluation
  Model validation against historical seasons
Documentation Requirements
  API documentation for all models & functions
  Data dictionary for all collected & generated features
  Model documentation including training methodology & evaluation
  User guide for running prediction generation
  Development journal capturing decisions & learning

## Slide 5
NBA Prediction System
Executive Summary
Deliverables
Final Project Artifacts:
  Source code repository with complete implementation
  Comprehensive documentation set
  Trained prediction models with validation results
  Sample prediction outputs
  Project presentation materials
Documentation Set:
  Project README and setup instructions
  Technical design documentation
  Data dictionary and feature explanations
  Model performance analysis
  User guide for system operations
Communication Plan
Stakeholder | Information Needs | Frequency | Method
Project sponsor | Progress Updates, key decisions | Bi-weekly | Status Report
Technical team | Technical decisions, implementation details | Weekly | Code reviews, technical notes
End Users | System capabilities, interpretation guide | Key-milestones | User documentation
Portfolio reviewers | Project overview, technical approach, results | Final | GitHub README, presentation